## Sheet1
Project Plan | Day/work
| 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17
Meeting1 | 2022-06-01: All members
Project Name select | bar: 2022-06-01
Meeting2 | 2022-06-02: All members
Manage the frontend(html page) | bar: 2022-06-02
Check the code | bar: 2022-06-02
Meeting3 | 2022-06-03: All members
frontend design(add CSS at style.css file) | 2022-06-03: 大山，沙姆
Check css code and other file as well as | bar: 2022-06-03
Again work at style.css | 2022-06-04: 大山，沙姆
Meeting4 | 2022-06-04: All Members
Check style.css file | bar: 2022-06-04
Meeting5 | 2022-06-05: All Members
Planing for next module | 2022-06-05: All Members
DOM manipulating | bar: 2022-06-06
Meeting6 | 2022-06-07: All Members
Set Condition with DOM and Frontend | bar: 2022-06-07
Meeting 7 | 2022-06-08: All Members
Problem solving Session | 2022-06-08: All Members
Work with functionality | bar: 2022-06-08
Finish the JavaScript All Activity | bar: 2022-06-09
Make ER and Class Diagram | bar: 2022-06-09
Edit Readme File And Add all Important topic | bar: 2022-06-10
Check All Work | 2022-06-11: All Members
Final Check HTML File | bar: 2022-06-12
Final Check CSS File | bar: 2022-06-13
Final Check JS File | bar: 2022-06-14
Final Check All File | bar: 2022-06-15
Final Check All Works | 2022-06-16: All Members
Final Meeting | 2022-06-17: All Members
Final Problem Solving Session | 2022-06-17: All Members
All Members